## Change Request Log
Change Request Log
Log every scope change request as it comes in. Fill in the light grey cells — Impact Level and Approval Status use dropdown lists. Replace or delete the example row before entering real data.
Project Name: |  | e.g. Finance System Upgrade
Change Control Owner: |  | e.g. M. Nowak
Reporting Period: |  | e.g. January 2025
Summary (Approved Changes)
Total Requests | Approved | Pending | Rejected | Budget Impact | Timeline Impact (days)
1 | 1 | 0 | 0 | 15000 | 10
Change Request Log
CR ID | Change Description | Requested By | Date Submitted | Impact Level | Budget Delta | Timeline Delta (days) | Approval Status | Approved By | Notes
CR-001 | Example: Add multi-currency support to invoice module | J. Alvarez | 2025-01-06 | High | 15000 | 10 | Approved | M. Nowak | Approved pending vendor quote confirmation
TOTAL (all requests, any status) |  |  |  |  | 15000 | 10
Legend
High impact / Rejected
Medium impact / Pending
Low impact / Approved
On Hold
Notes — Budget Delta and Timeline Delta (days) can be positive (increase) or negative (decrease/saving). "Budget Impact" and "Timeline Impact" in the Summary above total only Approved changes, since Pending and Rejected requests haven't actually affected the project yet.