## Dependency Register
Dependency Map — Register
Log every dependency between workstreams here. Dependency Type, Critical Path, and Status use dropdown lists. See the "Dependency Grid" tab for a visual matrix view of the same information.
Project Name: |  | e.g. Finance System Upgrade
Program / PM Owner: |  | e.g. M. Nowak
Reporting Date: |  | e.g. 2025-01-06
Summary
Total Dependencies | Critical Path | At Risk | Complete
1 | 1 | 0 | 0
Dependency Register
Dep. ID | Upstream Workstream | Downstream Workstream | Dependency Type | Description | Owner | Target Date | Critical Path? | Status | Notes
D-001 | Data Migration | UAT Testing | Finish-to-Start | Example: UAT cannot begin until data migration is complete and validated | R. Ionescu | 2025-02-03 | Yes | In Progress | Migration slipped 3 days; monitoring impact on UAT start
Legend
Critical path (Yes) / At Risk
In Progress
Not on critical path (No) / Complete
Not Started
Dependency types — Finish-to-Start: successor starts after predecessor finishes (most common). Start-to-Start: successor starts once predecessor starts. Finish-to-Finish: successor finishes only after predecessor finishes. Start-to-Finish: successor finishes only once predecessor starts (rare).

## Dependency Grid
Dependency Map — Grid
List each workstream once in the column below — the column headers to the right update automatically to match. Mark X where the row workstream is an upstream dependency for the column workstream; mark C instead of X if that dependency sits on the critical path. Diagonal cells are shaded grey (a workstream can't depend on itself). "Fan-out" and "Fan-in" totals on the right/bottom flag the most connected — and often highest-risk — workstreams.
Upstream ↓ / Downstream → | Workstream 1 | Workstream 2 | Workstream 3 | Workstream 4 | Workstream 5 | Workstream 6 | Workstream 7 | Workstream 8 | Workstream 9 | Workstream 10 | Fan-out (downstream count)
Workstream 1 | — | [9 empty] | 0
Workstream 2 |  | — | [8 empty] | 0
Workstream 3 |  |  | — | [7 empty] | 0
Workstream 4 |  |  |  | — | [6 empty] | 0
Workstream 5 |  |  |  |  | — | [5 empty] | 0
Workstream 6 | [5 empty] | — |  |  |  |  | 0
Workstream 7 | [6 empty] | — |  |  |  | 0
Workstream 8 | [7 empty] | — |  |  | 0
Workstream 9 | [8 empty] | — |  | 0
Workstream 10 | [9 empty] | — | 0
Fan-in (upstream count) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legend
X = standard dependency
C = critical-path dependency
— = not applicable (same workstream)
Read the grid as "row depends on / feeds into column": a mark in row 3, column 7 means Workstream 3 is an upstream dependency for Workstream 7. Workstreams with the highest Fan-out + Fan-in totals are the most interconnected — delays there are most likely to cascade, so treat them as candidate critical-path items even before formal schedule analysis.