## Milestone Tracker
Milestone Tracker Template
Fill in Planned Date as you plan the project, then Actual Date once each milestone completes. Variance and Status calculate and highlight automatically — Status turns red the moment a Planned Date passes with no Actual Date entered.
Project Name: |  | e.g. Finance System Upgrade
Project Manager: |  | e.g. M. Nowak
Reporting Date: |  | e.g. 2025-01-06
Summary
Total Milestones | Completed On Time | Completed Late | Delayed | Upcoming
1 | 1 | 0 | 0 | 0
Milestones by Phase
Milestone | Planned Date | Actual Date | Variance (days) | Status | Owner | Notes
PHASE 1: INITIATION
Example: Project charter approved | 2025-01-10 | 2025-01-09 | -1 | Completed On Time | M. Nowak | Approved a day early
PHASE 2: PLANNING
PHASE 3: EXECUTION
PHASE 4: CLOSURE
Legend
Delayed — planned date has passed with no actual date entered
Completed Late — actual date is after planned date
Completed On Time — actual date is on or before planned date
Upcoming — planned date is still in the future
Status and Variance recalculate automatically whenever you open the file or edit a date — "Delayed" is date-driven (compares Planned Date to today), so it updates on its own without you touching the row.
Formulas:
Upcoming = IF([Completed On Time]="","",IF([Completed Late]<>"",IF([Completed Late]<=[Completed On Time],"Completed On Time","Completed Late"),IF([Completed On Time]<TODAY(),"Delayed","Upcoming")))