## Backlog Prioritisation
Backlog Prioritisation Matrix
Score Business Value and Effort 1-5 for each item. Priority Score and Rank calculate automatically — higher Value for lower Effort ranks first (quick wins).
Backlog
Backlog Item | Business Value (1-5) | Effort (1-5) | Priority Score | Rank | MoSCoW | Notes
Add multi-currency support to checkout | 5 | 3 | 1.67 | 2 | Must
Redesign onboarding email templates | 3 | 1 | 3 | 1 | Should
Migrate reporting to new data warehouse | 4 | 5 | 0.8 | 4 | Must
Add dark mode to dashboard | 2 | 2 | 1 | 3 | Could
Refactor legacy auth module | 3 | 4 | 0.75 | 5 | Should
Legend (MoSCoW)
Must — non-negotiable for this release
Should — important but not release-blocking
Could — nice to have if time allows
Won't — explicitly out of scope this time
Priority Score = Business Value ÷ Effort. A high score means high value for relatively low effort (a quick win); use Rank alongside MoSCoW, not instead of it — a Rank-1 item that's tagged Won't this release stays Won't regardless of its score.

## Velocity Tracker
Velocity Tracker
Log Committed and Completed points each sprint. % Delivered, Rolling 3-Sprint Average, and the chart update automatically.
Summary
Average Velocity | Last Sprint Velocity | Best Sprint
30.7 | 35 | 35
Sprint History
Sprint | Committed Points | Completed Points | % Delivered | Rolling 3-Sprint Avg | Notes
Sprint 1 | 30 | 26 | 86.67% |  | First sprint with new team composition
Sprint 2 | 30 | 29 | 96.67%
Sprint 3 | 32 | 31 | 96.88% | 28.6667
Sprint 4 | 32 | 30 | 93.75% | 30 | One engineer out sick for 3 days
Sprint 5 | 34 | 33 | 97.06% | 31.3333
Sprint 6 | 34 | 35 | 102.9% | 32.6667 | Slightly ahead of plan

## Release Roadmap
Release Roadmap
Track planned releases and their key features. Status calculates automatically from Target Date and Actual Release Date, the same way as the other date-driven trackers in this toolkit.
Releases
Release | Key Features / Epics | Sprint Range | Target Date | Actual Release Date | Status
v2.1 | Multi-currency checkout, onboarding email redesign | Sprints 1-3 | 2025-02-14 | 2025-02-12 | Released On Time
v2.2 | Reporting data warehouse migration | Sprints 4-6 | 2025-04-04 | 2025-04-10 | Released Late
v2.3 | Dark mode, auth module refactor | Sprints 7-9 | 2025-05-23 |  | Delayed
v2.4 | Next planned release, not yet due | Sprints 10-12 | 2027-03-01 |  | Planned
Legend
Delayed — target date passed, not yet released
Released Late — released after target date
Released On Time
Planned — target date still in the future
Formulas:
Status = IF([Target Date]="","",IF([Actual Release Date]<>"",IF([Actual Release Date]<=[Target Date],"Released On Time","Released Late"),IF([Target Date]<TODAY(),"Delayed","Planned")))