## Gantt Chart
Multi-Workstream Project Planner — Gantt Chart
Enter Start/End dates and % Complete per task. The timeline bar, RAG Status, and the Workstream Summary above all calculate automatically from these two inputs.
Workstream Summary (RAG rollup)
Workstream | Overall RAG
Workstream 1 | Green
Workstream 2 | Green
Workstream 3 | Not Started
Workstream 4 | Amber
Workstream 5 | Red
Workstream 6 | Red
Workstream 7 | Green
Workstream 8 | Amber
Task Detail & Timeline
Workstream | Task | Owner | Start Date | End Date | % Complete | Critical Path? | RAG Status | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09
Workstream 1 | Data migration mapping complete | R. Ionescu | 2026-08-18 | 2026-09-17 | 75% | Yes | Green
Workstream 1
Workstream 1
Workstream 2 | Vendor contract finalized | M. Nowak | 2026-07-29 | 2026-08-18 | 100% | Yes | Green
Workstream 2
Workstream 2
Workstream 3 | UAT test cases drafted | J. Alvarez | 2026-09-17 | 2026-10-07 | 0% | No | Not Started
Workstream 3
Workstream 3
Workstream 4 | Training materials outline | T. Dinescu | 2026-08-23 | 2026-09-22 | 35% | No | Amber
Workstream 4
Workstream 4
Workstream 5 | Infrastructure provisioning | R. Ionescu | 2026-08-18 | 2026-09-12 | 30% | Yes | Red
Workstream 5
Workstream 5
Workstream 6 | Reporting requirements sign-off | M. Nowak | 2026-08-08 | 2026-09-02 | 60% | No | Red
Workstream 6
Workstream 6
Workstream 7 | Security review | J. Alvarez | 2026-08-28 | 2026-09-27 | 40% | Yes | Green
Workstream 7
Workstream 7
Workstream 8 | Change management plan | T. Dinescu | 2026-08-13 | 2026-09-12 | 70% | No | Amber
Workstream 8
Workstream 8
Legend
Red — behind schedule by >20%, or overdue and incomplete
Amber — behind schedule by 5-20%
Green — on schedule or ahead, or complete
Not Started — start date still in the future
RAG Status compares % Complete to where the task “should” be given today’s date and its Start/End dates. Critical Path tasks (marked Yes) render as red bars in the timeline regardless of their RAG status — that column flags schedule dependency risk, not current health.

## Resource Allocation
Resource Allocation Matrix
Enter each person's Available Capacity and their % allocation across the 8 workstreams. Total Allocated and Utilisation calculate automatically — see the Resource Capacity Planner resource for a full 15-person version with gap alerts.
Allocation
Team Member | Available Capacity | Workstream 1 | Workstream 2 | Workstream 3 | Workstream 4 | Workstream 5 | Workstream 6 | Workstream 7 | Workstream 8 | Total Allocated | Utilisation
R. Ionescu | 100% | 30% | 0% | 20% | 0% | 30% | 0% | 20% | 0% | 100% | 100%
M. Nowak | 100% | 0% | 40% | 0% | 0% | 0% | 30% | 0% | 0% | 70% | 70%
J. Alvarez | 80% | 0% | 0% | 50% | 0% | 0% | 0% | 40% | 0% | 90% | 112.5%
T. Dinescu | 100% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 40% | 90% | 90%

## Milestone Dashboard
Milestone Dashboard
One key milestone per workstream. Status calculates automatically — it turns red the moment a Planned Date passes with no Actual Date entered.
Summary
Total Milestones | Completed On Time | Completed Late | Delayed | Upcoming
8 | 1 | 1 | 2 | 4
Milestones
Workstream | Milestone | Planned Date | Actual Date | Status | Notes
Workstream 1 | Data migration complete | 2026-09-02 | 2026-09-01 | Completed On Time | Migrated a day ahead of plan
Workstream 2 | Vendor contract signed | 2026-08-18 | 2026-08-20 | Completed Late | Minor delay in legal review
Workstream 3 | UAT test cases approved | 2026-10-07 |  | Upcoming
Workstream 4 | Training rollout complete | 2026-09-22 |  | Upcoming
Workstream 5 | Infrastructure live | 2026-09-04 |  | Delayed | Overdue — provisioning delay, see Gantt Chart
Workstream 6 | Reporting sign-off | 2026-09-02 |  | Delayed | Overdue — stakeholder review pending
Workstream 7 | Security review passed | 2026-09-27 |  | Upcoming
Workstream 8 | Change management plan approved | 2026-09-12 |  | Upcoming
Legend
Delayed
Completed Late
Completed On Time
Upcoming
Formulas:
Upcoming = IF([Completed Late]="","",IF([Delayed]<>"",IF([Delayed]<=[Completed Late],"Completed On Time","Completed Late"),IF([Completed Late]<TODAY(),"Delayed","Upcoming")))