## Capacity & Allocation
Resource Capacity Planner
Enter each person's Available Capacity (usually 100% = full-time) and their % allocation per workstream — rename the workstream columns to match your programme. Total Allocated, Utilisation, and Status all calculate automatically.
Programme Name: |  | e.g. Finance System Upgrade
Period: |  | e.g. Q1 2025
Summary
Team Members | Overallocated | Gap (Underused) | OK | Average Utilisation
1 | 0 | 0 | 1 | 90%
Workstream Allocation Matrix
Team Member | Role | Available Capacity | Workstream 1 | Workstream 2 | Workstream 3 | Workstream 4 | Workstream 5 | Total Allocated | Utilisation | Status
J. Alvarez | Finance Lead | 100% | 40% | 30% | 20% | 0% | 0% | 90% | 90% | OK
Legend
Overallocated (utilisation > 100%)
Gap / Underused (utilisation < 80%)
OK (80-100% utilisation)
Utilisation = Total Allocated ÷ Available Capacity. A person available 50% (part-time) who is allocated 60% total is Overallocated (120%) even though 60% looks modest at a glance — always read Utilisation, not the raw Total Allocated percentage, when judging workload.

## Monthly Capacity View
Monthly Capacity View
Roll up total team capacity and demand month by month — useful for spotting a squeeze coming two or three months out, before it shows up in the current-period matrix. Enter each month’s totals as your plan evolves.
Monthly Rollup
Month | Total Available Capacity (FTE) | Total Demand (FTE) | Utilisation | Status
Example: January | 12 | 10.8 | 90% | OK
February | 12 | 11.5 | 95.83% | OK
March | 12 | 13.2 | 110% | Overallocated
April | 13 | 9.5 | 73.08% | Gap
May | 13
June | 13
Legend
Overallocated (demand exceeds capacity)
Gap (capacity going unused)
OK