## Instructions
RACI MATRIX TEMPLATE
MDD Business Consulting · Project Management Resource
WHAT IS A RACI MATRIX?
A RACI matrix defines who is Responsible, Accountable, Consulted, and Informed for each task or decision in a project. It eliminates ambiguity about roles and prevents tasks from falling through the cracks.
R | RESPONSIBLE The person or people who do the work. At least one R per task. Multiple people can share an R.
A | ACCOUNTABLE The one person who owns the outcome and has final decision authority. Only ONE A per task — no exceptions.
C | CONSULTED People whose input is sought before the work is done. Two-way communication. Can be multiple people.
I | INFORMED People kept updated on progress or decisions. One-way communication — they do not need to respond or approve.
HOW TO USE THIS TEMPLATE
Step 1: Go to the RACI Matrix tab. Enter your project name in cell B2.
Step 2: Replace the column headers (Row 5) with your team members' names or role titles.
Step 3: Replace the task names in column A with your project tasks or decisions.
Step 4: Enter R, A, C, or I in each cell. The cell will colour automatically via conditional formatting.
Step 5: Ensure every task has exactly one A (Accountable). The validation column will flag issues.
Step 6: Use the Worked Example tab to see a completed example before filling in your own.
Step 7: Delete the worked example rows from the RACI Matrix tab — they are for reference only.
GOLDEN RULES
▪ Every task must have exactly ONE Accountable (A). Two As means no one is truly accountable.
▪ Every task must have at least one Responsible (R). If no one is doing the work, the task won't get done.
▪ Avoid overloading one person with too many Rs — this creates bottlenecks.
▪ Keep the number of Cs low. Too many Consulteds slows down delivery.
▪ Inform sparingly — too many Is means people stop reading updates.
▪ The RACI should fit on one page when printed. If it doesn't, break the project into sub-workstreams.
MDD Business Consulting · mddbusinessconsulting.com · Free for individual use. Not for redistribution.

## RACI Matrix
RACI MATRIX
Project Name: [Enter Project Name Here]
|  | R Responsible |  |  |  |  | A Accountable |  |  |  |  | C Consulted |  |  |  |  | I Informed
| TASK / ACTIVITY / DECISION | Project Sponsor | Project Manager | Finance Lead | IT Lead | HR Lead | Operations Manager | Legal / Compliance | Change Manager | Business Analyst | Technical Architect | Vendor / Partner | Internal Audit | Communications Lead | Data Owner | End User Rep. | Workstream Lead A | Workstream Lead B | External Consultant | Executive Sponsor | PMO | VALIDATION
WORKSTREAM 1: Planning & Initiation
1 | Define project scope | [20 empty] | ⚠ No Accountable
2 | Develop project charter | [20 empty] | ⚠ No Accountable
3 | Identify stakeholders | [20 empty] | ⚠ No Accountable
4 | Establish project governance | [20 empty] | ⚠ No Accountable
5 | Approve project budget | [20 empty] | ⚠ No Accountable
6 | Define success criteria | [20 empty] | ⚠ No Accountable
WORKSTREAM 2: Design & Build
7 | Develop solution design | [20 empty] | ⚠ No Accountable
8 | Review and approve design | [20 empty] | ⚠ No Accountable
9 | Configure system / build solution | [20 empty] | ⚠ No Accountable
10 | Develop test scripts | [20 empty] | ⚠ No Accountable
11 | Conduct unit testing | [20 empty] | ⚠ No Accountable
12 | Conduct system integration testing | [20 empty] | ⚠ No Accountable
13 | Resolve defects | [20 empty] | ⚠ No Accountable
WORKSTREAM 3: Data & Integration
14 | Define data migration approach | [20 empty] | ⚠ No Accountable
15 | Extract and cleanse data | [20 empty] | ⚠ No Accountable
16 | Map data fields to target system | [20 empty] | ⚠ No Accountable
17 | Execute data migration | [20 empty] | ⚠ No Accountable
18 | Validate migrated data | [20 empty] | ⚠ No Accountable
WORKSTREAM 4: Change & Training
19 | Develop change management plan | [20 empty] | ⚠ No Accountable
20 | Conduct stakeholder impact assessment | [20 empty] | ⚠ No Accountable
21 | Design training materials | [20 empty] | ⚠ No Accountable
22 | Deliver end-user training | [20 empty] | ⚠ No Accountable
23 | Manage communications | [20 empty] | ⚠ No Accountable
WORKSTREAM 5: Go-Live & Hypercare
24 | Conduct user acceptance testing (UAT) | [20 empty] | ⚠ No Accountable
25 | Obtain UAT sign-off | [20 empty] | ⚠ No Accountable
26 | Define go-live cut-over plan | [20 empty] | ⚠ No Accountable
27 | Execute go-live | [20 empty] | ⚠ No Accountable
28 | Monitor and resolve hypercare issues | [20 empty] | ⚠ No Accountable
29 | Conduct post-implementation review | [20 empty] | ⚠ No Accountable
30 | Transition to BAU support | [20 empty] | ⚠ No Accountable
MDD Business Consulting · Project Management Resource · mddbusinessconsulting.com · Free for individual use. Not for redistribution.

## Worked Example
RACI MATRIX — WORKED EXAMPLE
Project: Finance System Implementation · Example for reference only
|  | R Responsible |  |  | A Accountable |  |  | C Consulted |  | I Informed
| TASK / ACTIVITY / DECISION | CFO | Finance Director | Project Manager | Finance Team | IT Team | Vendor | Internal Audit | Business Users | VALIDATION
WORKSTREAM 1: Planning & Initiation
1 | Define project scope | I | A | R | C | C | I | I | C | ✓ OK
2 | Develop project charter | A | C | R | I | I | I | I | I | ✓ OK
3 | Identify stakeholders | I | C | R | C | C | I | I | C | ⚠ No Accountable
4 | Approve project budget | A | R | C | I | I | I | C | I | ✓ OK
WORKSTREAM 2: Design & Build
5 | Develop solution design | I | C | R | C | R | R | I | C | ⚠ No Accountable
6 | Review and approve design | I | A | C | C | R | C | C | R | ✓ OK
7 | Configure system | I | I | C | I | A | R | I | I | ✓ OK
8 | Conduct user acceptance testing | I | A | C | C | C | R | C | R | ✓ OK
9 | Obtain UAT sign-off | I | A | C | R | I | I | I | R | ✓ OK
WORKSTREAM 3: Change & Governance
10 | Develop training materials | I | C | R | C | C | R | I | C | ⚠ No Accountable
11 | Deliver end-user training | I | I | A | R | C | C | I | R | ✓ OK
12 | Define audit trail requirements | I | C | C | R | C | I | A | I | ✓ OK
13 | Approve go-live decision | A | R | C | C | C | I | C | C | ✓ OK
14 | Post-implementation review | I | A | R | C | C | C | R | C | ✓ OK
MDD Business Consulting · Project Management Resource · mddbusinessconsulting.com · Free for individual use. Not for redistribution.