## Instructions
Finance Function Digitalisation Roadmap
A 12-month digitalisation roadmap planning tool for finance functions — current state assessment, priority initiative framework, resource requirement planner, and KPI dashboard.
How This Workbook Is Organised
– Current State Assessment: Score your finance function's digital maturity across 5 dimensions to establish your starting point.
– Priority Initiative Framework: Score candidate initiatives by impact and effort to decide what to tackle first.
– 12-Month Roadmap: A dynamic Gantt view — set a start month and duration per initiative and the timeline shades itself in.
– Resource Requirement Planner: Budget, internal hours, and vendor costs per initiative, with a rolled-up total.
– KPI Dashboard: Baseline, target, and current values for 8 measures that track whether the roadmap is actually working.
Colour Legend
– Blue text = an input cell you should fill in or edit for your own organisation.
– Black text = a formula — do not overtype, or the roadmap will stop calculating correctly.
– Green text = a link pulling data from another tab.
– Yellow fill = marks a key input or assumption cell.
Getting Started
1. Complete the ‘Current State Assessment’ honestly, as a team if possible — this sets a genuine baseline, not an aspirational one.
2. Review ‘Priority Initiative Framework’ and score each candidate initiative for your organisation — replace or add rows to fit your own context.
3. Use the resulting priority tiers to decide sequencing, then set start months and durations in ‘12-Month Roadmap’.
4. Fill in ‘Resource Requirement Planner’ to understand the real budget and internal capacity this roadmap requires.
5. Set baselines and targets in ‘KPI Dashboard’, then update ‘Current’ monthly to track real progress.
Important Notes
This workbook ships with illustrative sample initiatives and scores so you can see how it behaves — replace them with your own before using it to make real decisions.
A roadmap is a planning tool, not a contract. Revisit the Priority Framework and Roadmap tabs at least quarterly as priorities and constraints shift.

## Current State Assessment
Current State Assessment
Score each statement 1 (Rarely/Never) to 5 (Consistently/Fully) as a team, not just from one perspective.
Core Systems & ERP
Statement | Score (1-5)
Our core financial system is a single, integrated platform rather than a patchwork of disconnected tools. | 3
We can access accurate financial data in real time, not just after a manual export or reconciliation. | 3
Adding a new entity, cost centre, or reporting need doesn't require significant manual system rework. | 3
Our system vendor actively supports us with updates, security patches, and a credible product roadmap. | 3
Core Systems & ERP — Dimension Score | 12 | / 20
Data & Reporting
Statement | Score (1-5)
Standard management reports are generated automatically, not rebuilt manually each period. | 3
Stakeholders can self-serve common reporting needs without submitting a request to finance. | 3
We trust our data enough to act on a dashboard number without re-verifying it manually first. | 3
Report definitions (what a metric means) are documented and consistent across the organisation. | 3
Data & Reporting — Dimension Score | 12 | / 20
Process Automation
Statement | Score (1-5)
Routine reconciliations (bank, AR, AP) are substantially automated, not manually matched line by line. | 3
Month-end close relies on defined, largely automated workflows rather than ad hoc effort each period. | 3
Repetitive, high-volume tasks (data entry, standard journal entries) are automated or assisted by tools. | 3
We have actively evaluated AI or RPA tools for at least one real finance process, not just discussed it. | 3
Process Automation — Dimension Score | 12 | / 20
Team Skills & Capability
Statement | Score (1-5)
Our finance team is comfortable using the digital tools already available to them, not just tolerating them. | 3
At least one person on the team can build or maintain intermediate automation (Power Query, macros, scripts). | 3
The team receives some ongoing training on new digital tools, not just onboarding training once. | 3
The team sees digitalisation as making their work better, not primarily as a threat to their role. | 3
Team Skills & Capability — Dimension Score | 12 | / 20
Governance & Controls
Statement | Score (1-5)
We have a clear view of who has access to which financial systems and data, and it's reviewed periodically. | 3
Controls have been explicitly reviewed and updated for the automated processes we've already implemented. | 3
There is a named owner responsible for data governance and AI/tool usage decisions in finance. | 3
We have a clear process for evaluating a new digital tool before it touches real financial data. | 3
Governance & Controls — Dimension Score | 12 | / 20
OVERALL DIGITAL MATURITY SCORE
Core Systems & ERP | 12 | / 20
Data & Reporting | 12 | / 20
Process Automation | 12 | / 20
Team Skills & Capability | 12 | / 20
Governance & Controls | 12 | / 20
TOTAL MATURITY SCORE | 60 | / 100
MATURITY BAND
Interpretation | Developing — solid foundations, clear gaps to close

## Priority Initiative Framework
Priority Initiative Framework
Score each candidate initiative on Impact (1-5) and Effort (1-5). Priority Score and Tier calculate automatically — replace or add initiative rows to fit your own organisation.
Initiative | Impact (1-5) | Effort (1-5) | Priority Score | Priority Tier | Notes
Automate bank & cash reconciliation | 4 | 2 | 6 | Quick Win | Strong quick-win candidate — mature tools, low disruption.
AI-assisted month-end close checklist & workflow | 4 | 3 | 5 | Major Project | Builds on existing close process rather than replacing it.
Deploy Copilot / AI tools in Excel for reporting | 3 | 2 | 4 | Fill-In | Low-cost pilot; licensing already in place for many teams.
Rolling 13-week cash flow forecasting model | 4 | 2 | 6 | Quick Win | High visibility win for leadership and lenders.
Automate AP invoice processing (OCR / matching) | 5 | 4 | 6 | Major Project | High volume, high manual effort today — worth the build cost.
Automate AR collections & dunning workflow | 4 | 3 | 5 | Major Project | Directly improves cash position, not just efficiency.
RPA for repetitive journal entries | 3 | 3 | 3 | Deprioritise | Good candidate once close process is documented and stable.
Self-service BI dashboards for stakeholders | 4 | 4 | 4 | Major Project | Reduces ad hoc reporting requests once adopted.
Migrate to cloud ERP / upgrade core system | 5 | 5 | 5 | Major Project | Highest impact, highest effort — needs its own project plan.
E-signature & digital approval workflows | 3 | 1 | 5 | Fill-In | Fast to implement, meaningful control and speed benefit.
Automate variance analysis & flux reporting | 4 | 3 | 5 | Major Project | Pairs well with the BI dashboard initiative above.
Financial data warehouse / single source of truth | 5 | 5 | 5 | Major Project | Foundational for everything else — sequence carefully.
Implement continuous close practices | 4 | 4 | 4 | Major Project | Cultural and process change, not just a tool rollout.
Train finance team on AI tools & data literacy | 5 | 2 | 8 | Quick Win | Underrated lever — unlocks value from every other initiative.
Establish AI / data governance framework | 4 | 2 | 6 | Quick Win | Do this early — retrofitting governance later is harder.
PRIORITY TIER LOGIC
Quick Win |  | Impact ≥ 4, Effort ≤ 2 |  | Do these first — high return, low disruption.
Major Project |  | Impact ≥ 4, Effort ≥ 3 |  | Worth doing, but needs proper planning and resourcing.
Fill-In |  | Impact ≤ 3, Effort ≤ 2 |  | Nice to have — slot in around higher-priority work.
Deprioritise |  | Everything else |  | Low return for the effort required — revisit later if priorities shift.

## 12-Month Roadmap
12-Month Roadmap
Set a Start Month (1-12) and Duration (months) for each initiative — the timeline shades itself in automatically, colour-coded by Priority Tier from the framework tab.
Initiative | Start Month | Duration (Months) | Priority Tier | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Automate bank & cash reconciliation | 1 | 2 | Quick Win
AI-assisted month-end close checklist & workflow | 2 | 3 | Major Project
Deploy Copilot / AI tools in Excel for reporting | 1 | 2 | Fill-In
Rolling 13-week cash flow forecasting model | 3 | 2 | Quick Win
Automate AP invoice processing (OCR / matching) | 4 | 4 | Major Project
Automate AR collections & dunning workflow | 5 | 3 | Major Project
RPA for repetitive journal entries | 6 | 3 | Deprioritise
Self-service BI dashboards for stakeholders | 7 | 4 | Major Project
Migrate to cloud ERP / upgrade core system | 5 | 8 | Major Project
E-signature & digital approval workflows | 2 | 1 | Fill-In
Automate variance analysis & flux reporting | 7 | 3 | Major Project
Financial data warehouse / single source of truth | 6 | 6 | Major Project
Implement continuous close practices | 8 | 4 | Major Project
Train finance team on AI tools & data literacy | 1 | 3 | Quick Win
Establish AI / data governance framework | 1 | 2 | Quick Win
COLOUR KEY (matches Priority Tier from the framework tab)
Quick Win
Major Project
Fill-In
Deprioritise

## Resource Requirement Planner
Resource Requirement Planner
Estimate the internal and external resource each initiative needs. Total Cost and the rollup below calculate automatically.
Initiative | Internal FTE Hours / Week | External / Vendor Cost ($) | Software / Tool Cost ($) | Department(s) Involved | Total Cost ($)
Automate bank & cash reconciliation | 8 | 3000 | 6000 | Accounting, IT | 9000
AI-assisted month-end close checklist & workflow | 6 | 5000 | 4000 | Accounting, FP&A | 9000
Deploy Copilot / AI tools in Excel for reporting | 4 | 0 | 2400 | FP&A, Reporting | 2400
Rolling 13-week cash flow forecasting model | 6 | 4000 | 3000 | Treasury, FP&A | 7000
Automate AP invoice processing (OCR / matching) | 10 | 25000 | 15000 | AP, IT, Procurement | 40000
Automate AR collections & dunning workflow | 8 | 15000 | 8000 | AR, Credit Control | 23000
RPA for repetitive journal entries | 6 | 8000 | 5000 | Accounting, IT | 13000
Self-service BI dashboards for stakeholders | 8 | 12000 | 10000 | FP&A, Reporting, IT | 22000
Migrate to cloud ERP / upgrade core system | 20 | 150000 | 80000 | All Finance, IT | 230000
E-signature & digital approval workflows | 3 | 2000 | 1500 | Accounting, Legal | 3500
Automate variance analysis & flux reporting | 5 | 6000 | 4000 | FP&A, Reporting | 10000
Financial data warehouse / single source of truth | 15 | 60000 | 40000 | All Finance, IT | 100000
Implement continuous close practices | 10 | 5000 | 3000 | Accounting, FP&A | 8000
Train finance team on AI tools & data literacy | 4 | 8000 | 0 | All Finance, HR | 8000
Establish AI / data governance framework | 3 | 10000 | 2000 | Finance Leadership, IT | 12000
PROGRAMME TOTALS
Total Internal FTE Hours / Week (across all active initiatives) |  |  |  |  | 116
Total External / Vendor Cost |  |  |  |  | 313000
Total Software / Tool Cost |  |  |  |  | 183900
TOTAL PROGRAMME COST |  |  |  |  | 496900
Cost by Priority Tier:
Quick Win |  |  |  |  | 36000
Major Project |  |  |  |  | 442000
Fill-In |  |  |  |  | 5900
Deprioritise |  |  |  |  | 13000

## KPI Dashboard
KPI Dashboard
Set Baseline and Target when you start the roadmap. Update Current each month — Status and Progress calculate automatically.
KPI | Direction | Baseline | Target | Current | Progress | Status
% of Month-End Close Tasks Automated | Higher is Better | 20% | 70% | 35% | 30% | Behind
Days to Close (Calendar Days) | Lower is Better | 10 | 5 | 8 | 40% | Behind
Manual Journal Entries per Month | Lower is Better | 150 | 40 | 95 | 50% | On Track
% of Invoices Processed Touchless | Higher is Better | 15% | 60% | 28% | 28.89% | Behind
Average Report Generation Time (Hours) | Lower is Better | 12 | 2 | 7 | 50% | On Track
Reconciliation Exceptions per Month | Lower is Better | 45 | 15 | 30 | 50% | On Track
Finance Team Hours on Manual Data Entry / Week | Lower is Better | 25 | 8 | 16 | 52.94% | On Track
% of Forecasts Using Live/Automated Data Feeds | Higher is Better | 10% | 80% | 25% | 21.43% | Behind
SUMMARY
KPIs Achieved: |  | 0
KPIs On Track: |  | 4
KPIs Behind: |  | 4