## Stakeholder Register
STAKEHOLDER REGISTER
MDD Business Consulting · Project Management Resource
HOW TO USE: List every stakeholder. Score Power (1–5) and Interest (1–5). The Quadrant and Engagement Strategy populate automatically. Update the register at every project phase gate.
ID | Name | Role / Title | Organisation | Power (1–5) | Interest (1–5) | P×I Score | Quadrant | Engagement Strategy | Current Sentiment | Comms Frequency | Channel | Owner | Notes
SH01 | S. Thornton | Chief Financial Officer | Internal | 5 | 5 | 25 | Manage Closely | Engage proactively. Include in key decisions. Weekly touchpoint. | Supportive | Weekly | Steering Meeting |  | Executive sponsor — final decision authority on budget and go-live
SH02 | R. Patel | IT Director | Internal | 5 | 4 | 20 | Manage Closely | Engage proactively. Include in key decisions. Weekly touchpoint. | Neutral | Weekly | Steering Meeting |  | Controls infrastructure and system access — critical dependency
SH03 | J. Morrison | Head of FP&A | Internal | 4 | 5 | 20 | Manage Closely | Engage proactively. Include in key decisions. Weekly touchpoint. | Supportive | Weekly | Steering Meeting |  | Primary business owner of finance outputs — key design input
SH04 | L. Chen | Project Manager | Internal | 3 | 5 | 15 | Keep Informed | Structured communications. Involve in UAT and training. | Supportive | Monthly | Team Meeting |  | Delivery accountability — core team member
SH05 | A. Davies | Finance Manager | Internal | 3 | 5 | 15 | Keep Informed | Structured communications. Involve in UAT and training. | Neutral | Monthly | Team Meeting |  | Day-to-day finance user — key UAT participant
SH06 | M. Santos | Head of Internal Audit | Internal | 4 | 3 | 12 | Keep Satisfied | Regular updates on progress. Involve in milestone reviews. | Neutral | Bi-weekly | Project Update |  | Controls and governance sign-off — engage early on audit trail
SH07 | T. Williams | HR Director | Internal | 4 | 2 | 8 | Keep Satisfied | Regular updates on progress. Involve in milestone reviews. | Neutral | Bi-weekly | Project Update |  | Impacted by headcount and payroll data — keep informed
SH08 | C. Park | Legal & Compliance Manager | Internal | 3 | 3 | 9 | Monitor | Newsletter / general updates. No dedicated engagement needed. | Neutral | Quarterly | Email |  | GDPR and regulatory compliance input required
SH09 | D. Okafor | Finance Systems Lead | Internal | 3 | 5 | 15 | Keep Informed | Structured communications. Involve in UAT and training. | Supportive | Monthly | Team Meeting |  | Technical owner of finance systems — key technical resource
SH10 | B. Thompson | Senior Finance Analyst | Internal | 2 | 5 | 10 | Keep Informed | Structured communications. Involve in UAT and training. | Supportive | Monthly | Team Meeting |  | Power user — champion candidate for training and adoption
SH11 | F. Andersson | AP Team Leader | Internal | 2 | 4 | 8 | Keep Informed | Structured communications. Involve in UAT and training. | Resistant | Monthly | Team Meeting |  | High operational impact — address concerns early
SH12 | K. Nwosu | Accounts Receivable Manager | Internal | 2 | 4 | 8 | Keep Informed | Structured communications. Involve in UAT and training. | Neutral | Monthly | Team Meeting |  | Impacted by billing and AR process changes
SH13 | P. Larsson | Treasury Manager | Internal | 3 | 3 | 9 | Monitor | Newsletter / general updates. No dedicated engagement needed. | Neutral | Quarterly | Email |  | Cash flow and banking data — periodic consultation
SH14 | N. García | CEO | Internal | 5 | 2 | 10 | Keep Satisfied | Regular updates on progress. Involve in milestone reviews. | Supportive | Bi-weekly | Project Update |  | Executive awareness — no operational involvement required
SH15 | O. Fischer | Implementation Consultant | Vendor | 3 | 5 | 15 | Keep Informed | Structured communications. Involve in UAT and training. | Supportive | Monthly | Team Meeting |  | Primary vendor contact — weekly delivery checkpoint
SH16 | Y. Tanaka | Vendor Account Manager | Vendor | 3 | 3 | 9 | Monitor | Newsletter / general updates. No dedicated engagement needed. | Supportive | Quarterly | Email |  | Commercial relationship owner — escalation point
SH17 | E. Kowalski | External Auditor | External | 4 | 2 | 8 | Keep Satisfied | Regular updates on progress. Involve in milestone reviews. | Neutral | Bi-weekly | Project Update |  | Year-end audit implications — brief on system changes
SH18 | H. Mensah | Payroll Provider | External | 2 | 3 | 6 | Monitor | Newsletter / general updates. No dedicated engagement needed. | Neutral | Quarterly | Email |  | Integration dependency — confirm data feed requirements
SH19 | I. Rossi | Banking Partner | External | 2 | 2 | 4 | Monitor | Newsletter / general updates. No dedicated engagement needed. | Neutral | Quarterly | Email |  | Bank feed integration — limited engagement needed
SH20 | G. Nakamura | Board Audit Committee Chair | External | 5 | 2 | 10 | Keep Satisfied | Regular updates on progress. Involve in milestone reviews. | Neutral | Bi-weekly | Project Update |  | Governance oversight — annual briefing sufficient
© 2026 MDD Business Consulting · Free for individual use. Not for redistribution.

## Power Interest Grid
STAKEHOLDER POWER / INTEREST GRID
Plot each stakeholder by placing their ID in the correct quadrant based on Power (vertical axis) and Interest (horizontal axis) scores from the Register.
HIGH
|  | SH14 | SH20 |  |  |  | SH02 |  |  | SH01
|  | SH07 | SH17 | SH06 | [5 empty] | SH03
|  |  | KEEP SATISFIED ● High Power ● Low Interest | [5 empty] | MANAGE CLOSELY ● High Power ● High Interest
|  |  |  | SH08 | SH13 | SH16 |  |  |  | SH04 | SH05 | SH09 | SH15
LOW
|  | SH19 |  | SH18 |  |  | SH11 | SH12 |  | SH10
|  |  | MONITOR ● Low Power ● Low Interest | [5 empty] | KEEP INFORMED ● Low Power ● High Interest
INTEREST →
QUADRANT LEGEND
| MANAGE CLOSELY |  | Highest priority. Weekly engagement. Include in all key decisions.
| KEEP SATISFIED |  | Regular briefings. Involve in milestone reviews. Watch for resistance.
| KEEP INFORMED |  | Structured comms. Involve in UAT and training. Champion candidates.
| MONITOR |  | General project updates. No dedicated engagement plan needed.
© 2026 MDD Business Consulting · Free for individual use. Not for redistribution.

## Comms Frequency Guide
COMMUNICATION FREQUENCY GUIDE
MDD Business Consulting · Project Management Resource
Use this guide to design your stakeholder communication plan. Match each stakeholder's quadrant to the recommended channel, frequency, and content type. Adapt to your project context.
COMMUNICATION MATRIX BY QUADRANT
Quadrant | Frequency | Primary Channel | Meeting Type | Content | Key Message
MANAGE CLOSELY | Weekly | 1:1 meeting or steering group | Project steering meeting | Progress vs plan, risks, decisions required | Project is on track / at risk. Your input is needed on [X].
KEEP SATISFIED | Bi-weekly | Project update meeting | Project review or briefing | Milestone status, budget, key risks | The project is progressing. Next milestone is [X] on [date].
KEEP INFORMED | Monthly | Team meeting or email update | All-hands or department meeting | Progress summary, changes affecting the team | Here is what is happening and what it means for you.
MONITOR | Quarterly | Email or newsletter | Project newsletter | High-level status, major milestones | Project update: [one sentence summary].
COMMUNICATION PLANNING PRINCIPLES
Audience first | Write for the reader, not for yourself. A CFO and an end user need different levels of detail on the same topic.
One clear message | Every communication should have one primary message. If you have three things to say, send three communications — or prioritise.
Action or update | Every communication should be clearly one of two things: an update (no action needed) or a request (action clearly stated, with deadline and owner).
Frequency vs noise | Over-communicating desensitises stakeholders. Stick to the schedule. Only send additional communications when something has materially changed.
Escalation signals | Watch for stakeholders who stop responding. Non-response is often a sign of disengagement or emerging resistance — act early.
Sentiment tracking | Update the Sentiment column in the register after each significant interaction. A stakeholder moving from Supportive to Neutral is a warning sign.
Close the loop | When a stakeholder raises a question or concern, confirm when and how it was resolved. Unresolved items erode trust faster than any other factor.
STAKEHOLDER SENTIMENT GUIDE
Sentiment | Description | What to do
Supportive | Actively backing the project. Willing to advocate, give time, and remove blockers. Engage as a champion. |  |  | Give them visibility and involve in decisions. Protect their time.
Neutral | No strong view. May become supportive or resistant depending on their experience. Proactive engagement converts neutrals. |  |  | Schedule a 1:1 to understand their perspective. Address any concerns.
Resistant | Opposed to the project — openly or passively. Identify the root cause: concerns about impact, loss of control, or lack of information. Address directly. |  |  | Do not ignore — engage directly. Escalate to sponsor if resistance persists.
Unknown | No interaction yet. Do not assume positive sentiment. Prioritise early engagement to assess position. |  |  | Schedule an introductory conversation. Assess and update the register.
© 2026 MDD Business Consulting · Free for individual use. Not for redistribution.