## Slide 1
PREMIUM RESOURCE · AI & FINANCE AUTOMATION
Finance Function
Digitalisation Roadmap
A 12-Month Plan for Finance Transformation
Current state assessment · priority initiatives · resourcing · KPIs
MDD Business Consulting

## Slide 2
EXECUTIVE SUMMARY
Why This Matters Now
Finance functions are being asked to deliver deeper insight with the same headcount, while AI and automation tools mature faster than most teams can evaluate them. This roadmap turns that pressure into a sequenced, resourced 12-month plan — starting from an honest assessment of where the function actually stands today.
60/100
Current Digital
Maturity Score
15
Priority Initiatives
Identified
$497K
Total Programme
Investment
12
Months to Full
Execution
MDD Business Consulting · Finance Function Digitalisation Roadmap
2

## Slide 3
CURRENT STATE ASSESSMENT
Digital Maturity by Dimension
Each dimension scored 1–5 across 4 statements, for a maximum of 20 per dimension.
Chart: 
| Core Systems & ERP | Data & Reporting | Process Automation | Team Skills & Capability | Governance & Controls
Score | 14 | 10 | 9 | 14 | 13
MDD Business Consulting · Finance Function Digitalisation Roadmap
3

## Slide 4
BASELINE
Where We're Starting From
60
out of 100
DEVELOPING
Solid foundations,
clear gaps to close
Foundational
0–39
Emerging
40–59
Developing
60–79
Advanced
80–100
MDD Business Consulting · Finance Function Digitalisation Roadmap
4

## Slide 5
PRIORITY INITIATIVE FRAMEWORK
Impact vs. Effort
EFFORT →
IMPACT →
QUICK WIN
MAJOR PROJECT
FILL-IN
DEPRIORITISE
Each dot is one candidate
digitalisation initiative,
plotted by scored Impact
and Effort (1–5).
Quick Win
Major Project
Fill-In
Deprioritise
MDD Business Consulting · Finance Function Digitalisation Roadmap
5

## Slide 6
12-MONTH ROADMAP
Three Phases, Twelve Months
PHASE 1
Quick Wins
Months 1–3
PHASE 2
Core Build
Months 4–8
PHASE 3
Scale & Optimise
Months 9–12
M1
M2
M3
M4
M5
M6
M7
M8
M9
M10
M11
M12
Quick Wins build early momentum and free up capacity. Core Build tackles the higher-effort, higher-value initiatives once the team has tooling familiarity. Scale & Optimise closes out complex, cross-functional projects and locks in the operating model.
4
Quick Win initiatives
8
Major Project initiatives
2
Fill-In initiatives
MDD Business Consulting · Finance Function Digitalisation Roadmap
6

## Slide 7
PHASE 1 · MONTHS 1–3
Quick Wins
High impact, low effort — build momentum and free up capacity for what follows.
1
Automate bank & cash reconciliation
Mature tools, low disruption — the clearest starting point.
2
Rolling 13-week cash flow forecast
High visibility win for leadership and lenders alike.
3
Train finance team on AI tools & data literacy
Unlocks value from every other initiative on this roadmap.
4
Establish AI / data governance framework
Do this early — retrofitting governance later is much harder.
MDD Business Consulting · Finance Function Digitalisation Roadmap
7

## Slide 8
PHASE 2 · MONTHS 4–8
Core Build
Higher-effort initiatives that need proper planning — tackled once the team has tooling familiarity.
1
Automate AP invoice processing (OCR / matching)
High volume, high manual effort today — worth the build cost.
2
Automate AR collections & dunning workflow
Directly improves cash position, not just efficiency.
3
Self-service BI dashboards for stakeholders
Reduces ad hoc reporting requests once adopted.
4
Migrate to cloud ERP / upgrade core system
Highest impact, highest effort — runs as its own governed project.
MDD Business Consulting · Finance Function Digitalisation Roadmap
8

## Slide 9
PHASE 3 · MONTHS 9–12
Scale & Optimise
Complex, cross-functional projects that close out the programme and lock in the operating model.
1
Automate variance analysis & flux reporting
Pairs naturally with the BI dashboard work from Phase 2.
2
Financial data warehouse / single source of truth
Foundational for everything else — sequenced carefully, not first.
3
Implement continuous close practices
Cultural and process change, not just a tool rollout.
MDD Business Consulting · Finance Function Digitalisation Roadmap
9

## Slide 10
RESOURCE REQUIREMENTS
What This Roadmap Actually Costs
$497K
Total Programme
Cost
116
Internal FTE Hours
per Week
$313K
External / Vendor
Cost
$184K
Software / Tool
Cost
Investment by Priority Tier
Quick Win
$36K (7%)
Major Project
$442K (89%)
Fill-In
$6K (1%)
Deprioritise
$13K (3%)
MDD Business Consulting · Finance Function Digitalisation Roadmap
10

## Slide 11
KPIS & SUCCESS MEASURES
How We'll Know It's Working
Baseline and target for each measure — tracked monthly in the companion workbook's KPI Dashboard.
KPI | Baseline | Target
% of Month-End Close Tasks Automated | 20% | 70%
Days to Close (Calendar Days) | 10 | 5
Manual Journal Entries per Month | 150 | 40
% of Invoices Processed Touchless | 15% | 60%
Average Report Generation Time (Hrs) | 12.0 | 2.0
Reconciliation Exceptions per Month | 45 | 15
Finance Hours on Manual Entry / Week | 25.0 | 8.0
% of Forecasts Using Live Data Feeds | 10% | 80%
MDD Business Consulting · Finance Function Digitalisation Roadmap
11

## Slide 12
RISKS & MITIGATIONS
What Could Go Wrong — and the Plan for It
Risk | Why It Happens | Mitigation
Team capacity constraints | The team can't do this on top of day-to-day close work. | Sequence Quick Wins first to free up time before tackling Major Projects.
Data quality issues surface mid-project | Automation exposes existing data problems it didn't create. | Budget time in each initiative specifically for data clean-up, not just tool setup.
Vendor or implementation delays | External dependencies push back the timeline. | Build buffer into Major Project durations; avoid daisy-chaining dependent initiatives.
Change resistance from the team | Automation is perceived as a threat, not a help. | Involve the team in initiative selection and lead with the training initiative early.
Budget overrun on complex initiatives | ERP migration and data warehouse projects are historically hard to estimate. | Treat the two highest-effort initiatives as their own separately governed projects.
MDD Business Consulting · Finance Function Digitalisation Roadmap
12

## Slide 13
NEXT STEPS
Turning This Into Action
1
Complete the Current State Assessment as a full finance team, not just leadership.
2
Confirm the Priority Framework scoring reflects your organisation's real constraints, not the illustrative example.
3
Agree the Phase 1 Quick Wins with a named owner and start date for each.
4
Review resourcing with finance leadership before committing to Phase 2 and Phase 3 timing.
info@mddbusinessconsulting.com
MDD Business Consulting